## Gantt Chart - Manual Duration
Omschrijving opdracht | Begin datum | Eind datum | Dagen | Voorbij | Te gaan | Gedaan | Start datum in numeric vorm | 43800
Timesheet | 2019-12-01 | 2020-01-05 | 35 | 3.5 | 31.5 | 10%
Briefing | 2019-12-01 | 2019-12-02 | 1 | 1 | 0 | 100%
Planning | 2019-12-02 | 2019-12-03 | 1 | 1 | 0 | 100%
Analyse | 2019-12-03 | 2019-12-05 | 2 | 2 | 0 | 100%
Requirements | 2019-12-04 | 2019-12-05 | 1 | 0 | 1 | 0%
Datamodel | 2019-12-06 | 2019-12-08 | 2 | 0 | 2 | 0%
Sitemap Website | 2019-12-07 | 2019-12-08 | 1 | 0 | 1 | 0%
Wireframes Website | 2019-12-08 | 2019-12-09 | 1 | 0 | 1 | 0%
Wireflow Mobile Web App | 2019-12-09 | 2019-12-10 | 1 | 0 | 1 | 0%
Style Guide | 2019-12-10 | 2019-12-12 | 2 | 0 | 2 | 0%
Visual Designs Website | 2019-12-12 | 2019-12-14 | 2 | 0 | 2 | 0%
Visual Designs Web App | 2019-12-14 | 2019-12-16 | 2 | 0 | 2 | 0%
Developen | 2019-12-09 | 2020-01-05 | 27 | 0 | 27 | 0%
Code Snippets | 2019-12-28 | 2019-12-29 | 1 | 0 | 1 | 0%
Schermafbeeldingen | 2019-12-29 | 2019-12-30 | 1 | 0 | 1 | 0%
Handleiding Website | 2019-12-30 | 2019-12-31 | 1 | 0 | 1 | 0%
Handleiding Mobile Web App | 2019-12-31 | 2020-01-01 | 1 | 0 | 1 | 0%
Deployment Guide | 2020-01-01 | 2020-01-02 | 1 | 0 | 1 | 0%
Productiedossier samenstellen | 2020-01-02 | 2020-01-03 | 1 | 0 | 1 | 0%
Schermopname | 2020-01-03 | 2020-01-04 | 1 | 0 | 1 | 0%
Presentatie | 2020-01-04 | 2020-01-05 | 1 | 0 | 1 | 0%
[7 empty] | Key: | Calculated Cell | Manual Entry Cell
[8 empty] | These cells will be automatically calculated based on the inputs on other cells. | These cells require manual input so the calculated cells have data to work with.